Name: Dory Thrasher

Project Name: Thesis Advising Metaproject

Date: Dec 22, 2025

Section A: What I accomplished in the past week

- Confirmed that all students submitted complete final proposals to the Google Drive

- Downloaded all final proposals to my desktop

- Reviewed all proposals at a high level

- Submitted final grades for first semester

- Completed in-depth review 3 of 7 proposals and typed up comments

- Created status update template

- Distributed status update template

Section B: What I had planned to get done, but didn’t get to

- Remind students about submitting the status updates

Section C: Tasks to complete in the next week

- In-depth review of final 4 proposals

- Send comments to all students

- Review additional documents shared by Student A

- Schedule second semester kickoff meeting (virtual)

- Plan agenda for kickoff meeting

Section D: Challenges/issues/obstacles

| Challenge | Approach | Do you want to discuss this? |
| --- | --- | --- |
| Not sure if the status update template will be helpful to students | Have them use it for a few weeks, ask for feedback. | Possibly, will follow up |
| Don’t have a university zoom account for virtual kickoff meeting. | Use Google Meet. | Nope, I have it under control |
| I don’t know where students are at with regards to their IRB approval status | Reach out by email | Yes, that would be helpful |