# Weekly Thesis Status Update

Name: Daniel Hardesty Lewis

Project Name: Predicting Zoning Opposition

Date: Mar 02, 2026

# Section A: What I accomplished in the past week

Conducted 5 research interviews with stakeholders out of my target of 10, covering key categories:

City Officials or Planners: Jonathan Tomko, Marla Torrado, Annick Beaudet

Housing Advocates: Felicity Maxwell

Residential Developers / Real Estate: Alina Carnahan

Completed full outline skeleton for all chapters, integrating quantitative modeling with qualitative interviews.

Drafted the Methodology chapter focusing on the complete data cleaning and acquisition pipeline.

Finalized Project One-Pager with AI forecasting hook.

Converted IRB Protocol to PDF with professional formatting.

Standardized EARS files (2019-2025), renamed Bibliography folders, and completed directory hygiene.

# Section B: What I had planned to get done, but didn't get to

Interview follow-up (Phase 2) for non-responders.

Sending finalized, personalized invitations to the Columbia reader shortlist.

Training baseline XGBoost/Regression preliminary models.

# Section C: Tasks to complete in the next week

Incorporate personalization from Reference PDF for 15 non-responders and execute via fetch_self_outreach.py to secure the remaining 5 interviews.

Send reader outreach invitations.

Schedule mid-February/March advisor check-in meeting.

Train preliminary models on confirmed 2019-2025 longitudinal dataset and draft preliminary results.

# Section D: Challenges/issues/obstacles

| Challenge | Approach | Do you want to discuss this? |
| --- | --- | --- |
| Need to locate/confirm layout files for EARS data dictionaries (especially 2018) | Review older archives or request from TCAD directly | No, I am handling it |
| Establishing automated backup for large excluded data files | Automate transfers to G: Drive/S3 | No |

Let me know if you need anything else! I have also attached the updated outline and methodology chapter drafts to the email.