Subject: Thesis Progress Update - Daniel Hardesty Lewis (Feb 1, 2026)

Hi Dory,

Here is my weekly status update.

______________________________

Name: Daniel Hardesty Lewis

Project Name: Thesis - Predicting Zoning Opposition

Date: Feb 1, 2026

SECTION A: ACCOMPLISHMENTS (PAST WEEK)

Data Acquisition (2019-2025): Downloaded and processed the Longitudinal Appraisal Dataset. This now covers 7 full years of owner/parcel data for the analysis.

Committee Outreach: Finished the Reader Shortlist & Outreach Strategy and drafted personalized invitations for a slate of candidates spanning Real Estate Finance, Urban Planning, and Applied Data Science at Columbia and elsewhere.

Interview Campaign (Phase 2 - Non-Responder Follow-up): Followed up on the initial outreach from Jan 23; 15 key stakeholders haven't responded. I am doing the following:

Development: Completed Personalization Research to identify alternative email addresses or ways of getting in contact with them.

Action: Scripted and queued Phase 2 Drafts using such personalizations.

SECTION B: PLANNED BUT INCOMPLETE

Methodology Draft: Pushed this back to focus on getting the data effectively secured first. Will draft this week.

SECTION C: NEXT WEEK TASKS

Send Outreach Emails: Send the invitations to secure a committee member by mid-Feb.

Draft Methodology Chapter: Write up the data pipeline and cleaning steps.

SECTION C2: OUTLOOK (2 WEEKS AHEAD)

Preliminary Models: Train baseline models on the confirmed 2019-2025 dataset.

Data Chapter: Draft the Data Chapter.

Literature Review: Synthesize comparative zoning theses.

Target Milestone: Advisor check-in mid-February.

SECTION D: CHALLENGES & OBSTACLES

None at this time.

PROGRESS LINK:

Interactive Project Repo (GitHub)

Detailed Master TODO List

Full Update Document (G: Drive): [PLEASE RIGHT CLICK FILE IN G:\My Drive AND PASTE LINK HERE]

______________________________

Best,

Daniel