Name: Daniel Hardesty Lewis

Project Name: Predicting NIMBYism

Date: Feb 2, 2026

Section A: What I accomplished in the past week

• Data Collection (2019-2025): Downloaded and processed the Longitudinal Appraisal Dataset. This now covers 7 full years of owner/parcel data.

• Finding Readers: Finished the Reader Shortlist and wrote personalized emails to candidates in Real Estate Finance, Urban Planning, and Data Science.

• Interview Follow-up: Found alternative contacts for the 15 non-responders and prepared personalized follow-ups (sending Feb 4).

Section B: What I had planned to get done, but didn’t get to

• Methodology Draft: Delayed this to finish downloading the data first.

Section C: Tasks to complete in the next week

• Send Emails: Send the invitations to potential readers.

• Draft Methodology: Write up the data collection and cleaning steps.

• Preliminary Models: Train baseline models on the 2019-2025 dataset.

• Initial Data Analysis: Begin drafting the Data Chapter findings.

Section D: Challenges/issues/obstacles

| Challenge | Approach | Do you want to discuss this? |
| --- | --- | --- |
| 15 non-responders from Jan 23 outreach | Found alternative emails and wrote new drafts. | Possibly, will follow up |
| Can't find EARS Data Dictionaries (Confirming all years) | Searching for layout files; might have to parse manually. | Nope, I have it under control |
| Finding the time to manage all these emails | Prioritizing automation and batching drafts. | Yes, that would be helpful |

______________________________

PROGRESS LINK:

Interactive Project Repo (GitHub)

Detailed Master TODO List

Full Update Document (G: Drive): [PLEASE RIGHT CLICK FILE IN G:\My Drive AND PASTE LINK HERE]